## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Authentication service | Francesco Saverio Sconocchia Pisoni | 10 | 10 | 0 |  |  |  |  | 100%
1.1 | DB Creation | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-08 | 2024-11-09 | 2 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
1.2 | Environment Creation | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-08 | 2024-11-08 | 1 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
1.3 | JWT setting | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 1 | 2024-11-09 | 2024-11-09 | 1 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
1.4 | JWT creation and providing | Francesco Saverio Sconocchia Pisoni | 4 | 4 | 0 | 1 | 2024-11-08 | 2024-11-09 | 2 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
1.5 | Tests auth | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 1 | 2024-11-09 | 2024-11-09 | 1 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
2 | User Profile service | Francesco Saverio Sconocchia Pisoni | 14 | 14 | 0 |  |  |  |  | 100%
2.1 | SignUp form creation | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 2 | 2024-12-05 | 2024-12-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 R to WEEK 4 F
2.2 | SignUp Data Validation | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-09 | 2024-11-09 | 1 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
2.3 | SignIn form creation | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 2 | 2024-12-05 | 2024-12-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 R to WEEK 4 F
2.4 | SignIn Data Validation | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-09 | 2024-11-09 | 1 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
2.5 | User's data insertion | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-09 | 2024-11-12 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
2.6 | Profile form creation | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 2 | 2024-12-05 | 2024-12-06 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 R to WEEK 4 F
2.7 | Delete profile | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-17 | 2024-11-17 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
2.8 | Update profile | Francesco Saverio Sconocchia Pisoni | 4 | 4 | 0 | 1 | 2024-11-18 | 2024-11-20 | 3 | 100% | bar: WEEK 2 T to WEEK 3 W
3 | RabbitMQ Service | Francesco Saverio Sconocchia Pisoni | 9 | 9 | 0 |  |  |  |  | 100%
3.1 | RabbitMQ service | Francesco Saverio Sconocchia Pisoni | 4 | 4 | 0 | 1 | 2024-11-12 | 2024-11-13 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
3.2 | Message consumer | Francesco Saverio Sconocchia Pisoni | 4 | 4 | 0 | 1 | 2024-11-13 | 2024-11-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
3.3 | Message insertion | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-13 | 2024-11-13 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4 | Notification Service | Francesco Saverio Sconocchia Pisoni | 4 | 4 | 0 |  |  |  |  | 100%
4.1 | Notification service | Francesco Saverio Sconocchia Pisoni | 2 | 2 | 0 | 1 | 2024-11-14 | 2024-11-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4.2 | Filters | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-14 | 2024-11-14 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4.3 | Notification implementation | Francesco Saverio Sconocchia Pisoni | 1 | 1 | 0 | 1 | 2024-11-14 | 2024-11-15 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
5 | Shopping List Service | Giulio Caporro | 32 | 32 | 0 |  |  |  |  | 100%
5.1 | Create Shopping List | Giulio Caporro | 6 | 6 | 0 | 1 | 2024-11-08 | 2024-11-09 | 2 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
5.2 | Update Shopping List | Giulio Caporro | 5 | 5 | 0 | 1 | 2024-11-08 | 2024-11-10 | 3 | 100% | bar: WEEK 1 F; WEEK 2 T to WEEK 2 F
5.3 | Delete Shopping List | Giulio Caporro | 4 | 4 | 0 | 1 | 2024-11-11 | 2024-11-13 | 3 | 100% | bar: WEEK 1 F to WEEK 2 F
5.4 | Add Quantity Selection | Giulio Caporro | 3 | 3 | 0 | 1 | 2024-11-12 | 2024-11-13 | 2 | 100%
5.5 | Searching shoppingList | Giulio Caporro | 3 | 3 | 0 | 1 | 2024-11-13 | 2024-11-14 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
5.6 | Create Delete Option in Shopping List | Giulio Caporro | 5 | 5 | 0 | 1 | 2024-11-14 | 2024-11-15 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
5.7 | Implement Ingredient Addition | Giulio Caporro | 6 | 6 | 0 | 1 | 2024-11-15 | 2024-11-16 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F
6 | Storage Service | Giulio Caporro | 80 | 80 | 0 |  |  |  |  | 100%
6.1 | Create Storage Model | Giulio Caporro | 6 | 6 | 0 | 2 | 2024-12-01 | 2024-12-01 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 M
6.2 | Implement CRUD operations | Giulio Caporro | 8 | 8 | 0 | 2 | 2024-12-02 | 2024-12-02 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 M
6.3 | JWT Integration for Security | Giulio Caporro | 7 | 7 | 0 | 2 | 2024-12-03 | 2024-12-03 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 T
6.4 | Create Scheduled Task Service | Giulio Caporro | 7 | 7 | 0 | 2 | 2024-12-03 | 2024-12-05 | 3 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 T to WEEK 4 R
6.5 | Notification Integration | Giulio Caporro | 8 | 8 | 0 | 2 | 2024-12-06 | 2024-12-11 | 6 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 F to WEEK 5 W
6.6 | Add Quantity Selection for Storage | Giulio Caporro | 2 | 2 | 0 | 2 | 2024-12-07 | 2024-12-08 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 4 F
6.7 | Enable Notifications for Expirations | Giulio Caporro | 25 | 25 | 0 | 2 | 2024-12-12 | 2024-12-13 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 R to WEEK 5 F
6.8 | Display Ingredient Storage | Giulio Caporro | 5 | 5 | 0 | 2 | 2024-12-13 | 2024-12-15 | 3 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 F to WEEK 6 T
6.9 | Implement UI | Lorenzo Tanzi | 12 | 12 | 0 | 3 | 2024-12-18 | 2025-01-09 | 23 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 7 W to WEEK 7 F; WEEK 10 R
7 | Recipes&Ingredients Service | Lorenzo Tanzi | 55 | 55 | 0 |  |  |  |  | 100%
7.1 | Home page view | Lorenzo Tanzi | 10 | 10 | 0 | 3 | 2024-12-18 | 2024-12-19 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 7 W to WEEK 7 R
7.2 | Search view | Lorenzo Tanzi | 7 | 7 | 0 | 3 | 2024-12-18 | 2024-12-19 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 7 W to WEEK 7 R
7.3 | Recipe API request "by recipe name" | Lorenzo Tanzi | 10 | 10 | 0 | 3 | 2024-12-18 | 2024-12-20 | 3 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 7 W to WEEK 7 F
7.4 | Recipe API request "by ingredient" | Lorenzo Tanzi | 10 | 10 | 0 | 3 | 2024-12-27 | 2025-01-05 | 10 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 8 F to WEEK 9 M
7.5 | Insertion of saved recipe | Lorenzo Tanzi | 4 | 4 | 0 | 3 | 2025-01-05 | 2025-01-08 | 4 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 9 F to WEEK 10 M
7.6 | Saved recipes view | Lorenzo Tanzi | 4 | 4 | 0 | 3 | 2025-01-05 | 2025-01-09 | 5 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 9 F; WEEK 10 T; WEEK 10 R
7.7 | Recipe view | Lorenzo Tanzi | 6 | 6 | 0 | 3 | 2025-01-07 | 2025-01-08 | 2 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 10 T to WEEK 10 W
7.8 | Removal of saved recipe | Lorenzo Tanzi | 4 | 4 | 0 | 3 | 2025-01-08 | 2025-01-08 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 10 W; WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 204 | 204 | 0 | 50 | 4.08 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 204 | 199.92 | 195.84 | 191.76 | 187.68 | 183.6 | 179.52 | 175.44 | 171.36 | 167.28 | 163.2 | 159.12 | 155.04 | 150.96 | 146.88 | 142.8 | 138.72 | 134.64 | 130.56 | 126.48 | 122.4 | 118.32 | 114.24 | 110.16 | 106.08 | 102 | 97.92 | 93.84 | 89.76 | 85.68 | 81.6 | 77.52 | 73.44 | 69.36 | 65.28 | 61.2 | 57.12 | 53.04 | 48.96 | 44.88 | 40.8 | 36.72 | 32.64 | 28.56 | 24.48 | 20.4 | 16.32 | 12.24 | 8.16 | 4.08 | -1.7764e-13 | -4.08 | -8.16 | -12.24 | -16.32 | -20.4 | -24.48 | -28.56 | -32.64 | -36.72
[10 empty] | ESTIMATE | 204 | 196 | 192 | 187 | 179 | 175 | 163 | 159 | 157 | 153 | 145 | 143 | 141 | 139 | 135 | 129 | 121 | 117 | 113 | 111 | 109 | 105 | 101 | 97 | 89 | 81 | 77 | 72 | 70 | 67 | 63 | 57 | 50 | 46 | 42 | 38 | 36 | 32 | 28 | 26 | 24 | 22 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4435
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 8 | 4 | 5 | 8 | 4 | 12 | 4 | 2 | 4 | 8 | 2 | 2 | 2 | 4 | 6 | 8 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 8 | 8 | 4 | 5 | 2 | 3 | 4 | 6 | 7 | 4 | 4 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | 4 | 4 | 6 | 4 | 4 | [14 empty] | 204
[10 empty] | HRS REMAINING | 196 | 192 | 187 | 179 | 175 | 163 | 159 | 157 | 153 | 145 | 143 | 141 | 139 | 135 | 129 | 121 | 117 | 113 | 111 | 109 | 105 | 101 | 97 | 89 | 81 | 77 | 72 | 70 | 67 | 63 | 57 | 50 | 46 | 42 | 38 | 36 | 32 | 28 | 26 | 24 | 22 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4231
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
H | 1 | DB | DB Creation | create the DB by following the ER diagram | Francesco Saverio Sconocchia Pisoni | 1 | Completed |  | Not Started | 1
H | 1 | Environment | Environment Creation | Create the springboot project for authentication and user profile services and the docker-compose file | Francesco Saverio Sconocchia Pisoni | 1 | Completed |  | In Progress | 2
M | 1 | Authentication | JWT setting | create the jwt authentication system | Francesco Saverio Sconocchia Pisoni | 4 | Completed |  | Completed | 4
L | 1 | SignUp | SignUp form creation | create the view for the sign up phase | Francesco Saverio Sconocchia Pisoni | 2 | Completed |  |  | 8
L | 1 | SignUp | SignUp Data Validation | validate the correctness of the user's data | Francesco Saverio Sconocchia Pisoni | 1 | Completed |  |  | 16
H | 1 | SignUp | User's data insertion | insert user's data in the DB once validated | Francesco Saverio Sconocchia Pisoni | 1 | Completed |  |  | 24
L | 1 | SignIn | SignIn form creation | create the view for the sign in phase | Francesco Saverio Sconocchia Pisoni | 2 | Completed |  |  | 40
L | 1 | SignIn | SignIn Data Validation | validate the correctness of the user's data | Francesco Saverio Sconocchia Pisoni | 1 | Completed |  |  | 80
H | 1 | SignIn | JWT creation and providing | create the JWT token and provides it to the user | Francesco Saverio Sconocchia Pisoni | 4 | Completed
L | 1 | Profile | Profile form creation | create the view of the user's profile | Francesco Saverio Sconocchia Pisoni | 2 | Completed
M | 1 | Profile | Delete profile | delete user's data if requested by the user | Francesco Saverio Sconocchia Pisoni | 1 | Completed
M | 1 | Profile | Update profile | update and validate the user's data if changed by the user | Francesco Saverio Sconocchia Pisoni | 4 | Completed
H | 1 | Message | Message consumer | create the function which retrieves the messages from the queue | Francesco Saverio Sconocchia Pisoni | 4 | Completed
L | 1 | Test | Tests auth | create the unit tests for the authentication system routes | Francesco Saverio Sconocchia Pisoni | 2 | Completed
H | 1 | RabbitMQ | RabbitMQ service | Create the microservice of RabbitMQ with its configuration file | Francesco Saverio Sconocchia Pisoni | 4 | Completed
L | 1 | Notification | Notification service | Create the Notification project | Francesco Saverio Sconocchia Pisoni | 2 | Completed
M | 1 | Notification | Filters | Set the security configurations of the Notification service | Francesco Saverio Sconocchia Pisoni | 1 | Completed
M | 1 | Notification | Notification implementation | Create and implement the api routes of the Notification service | Francesco Saverio Sconocchia Pisoni | 1 | Completed
M | 1 | Message | Message insertion | create the function which sends the messages from the queue | Francesco Saverio Sconocchia Pisoni | 1 | Completed
H | 2 | Shopping List | Create shopping list | Develop the view for the shopping list | Giulio Caporro | 4 | Completed
H | 2 | Shopping List | Implement Ingredient Selection | Code the functionality to allow users to select multiple ingredients from the shopping list. | Giulio Caporro | 2 | Completed
H | 2 | Shopping List | Add Quantity Selection | Add functionality for users to specify quantities of each selected ingredient before moving to storage. | Giulio Caporro | 4 | Completed
H | 2 | Shopping List | Create Delete Option in Shopping List View | Add a delete option next to each ingredient in the shopping list view. | Giulio Caporro | 1 | Completed
H | 2 | Shopping List | Implement Ingredient Deletion Function | Code the function that deletes selected ingredients from the shopping list in the database. | Giulio Caporro | 4 | Completed
M | 2 | Shopping List | Validation for Delete Action | Add validation to confirm the deletion action (ask for confirmation if multiple items are selected). | Giulio Caporro | 2 | Completed
M | 2 | Shopping List | Update Shopping List Display | Refresh the shopping list view to reflect changes after ingredients are deleted. | Giulio Caporro | 1 | Completed
H | 2 | Shopping List | Move Ingredients to Storage | Code the functionality to move ingredients from the shopping list to the ingredients storage, updating quantities. | Giulio Caporro | 8 | Completed
M | 2 | Shopping List | Validate Quantity Update | Add a validation step to ensure that moved ingredients update the quantity correctly in storage. | Giulio Caporro | 4 | Completed
H | 2 | Shopping List | Display Shopping List Details | Develop a feature to display detailed information for each shopping list, including items and quantities. | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | Create Storage Model | Implement the data model for the storage service | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | Implement CRUD operations | Create the basic CRUD operations for the storage service | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | JWT Integration for Security | Secure the storage service endpoints using JWT-based authentication | Giulio Caporro | 8 | Completed
H | 3 | Storage Service | Create Scheduled Task Service | Develop a scheduled task to check for expired products and perform notifications | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | Notification Integration | Integrate the notification service to alert users about expired products | Giulio Caporro | 8 | Completed
H | 3 | Storage Service | Implement UI | Design and implement the user interface for managing the storage service | Lorenzo Tanzi | 8 | Completed
H | 3 | Storage Service | Set Expiration Date for Ingredients | Add functionality to allow users to set expiration dates for ingredients in their storage. | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | Enable Notifications for Expirations | Code the logic to send notifications 1 day before an ingredient expires. | Giulio Caporro | 4 | Completed
H | 3 | Storage Service | Add Quantity Selection for Storage | Develop functionality to allow users to set and update the quantity of each ingredient in storage. | Giulio Caporro | 2 | Completed
H | 3 | Storage Service | Display Ingredient Storage | Create a feature to display all ingredients available in the user's storage, along with their details. | Giulio Caporro | 4 | Completed
L | 1 | Search recipes | Home page view | create the view for the home page | Lorenzo Tanzi | 4 | Completed
H | 1 | Search recipes | Search view | create view for search results | Lorenzo Tanzi | 4 | Completed
M | 1 | Search recipes | Recipe API request "by recipe name" | implement API request by recipe name and response management | Lorenzo Tanzi | 2 | Completed
H | 1 | Search recipes | Recipe API request "by ingredient" | implement API request by ingredient and response management | Lorenzo Tanzi | 4 | Completed
H | 2 | Save recipes | Insertion of saved recipe | implement query to insert recipes into favourites recipes | Lorenzo Tanzi | 4 | Completed
H | 2 | Save recipes | Saved recipes view | create view to display all saved recipes | Lorenzo Tanzi | 2 | Completed
L | 2 | Search recipes | Recipe view | create view to display all information of a recipe | Lorenzo Tanzi | 4 | Completed
H | 2 | Save recipes | Removal of saved recipe | implement query to delete recipes from favourites recipes | Lorenzo Tanzi | 4 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
DB Creation | create the DB by following the ER diagram | Francesco Saverio Sconocchia Pisoni | 2024-10-30
Environment Creation | Create the springboot project for authentication and user profile services and the docker-compose file | Francesco Saverio Sconocchia Pisoni | 2024-10-30
JWT setting | create the jwt authentication system | Francesco Saverio Sconocchia Pisoni | 2024-11-06
SignUp form creation | create the view for the sign up phase | Francesco Saverio Sconocchia Pisoni | 2024-10-30
SignUp Data Validation | validate the correctness of the user's input data | Francesco Saverio Sconocchia Pisoni | 2024-10-30
User's data insertion | insert user's data in the DB once validated | Francesco Saverio Sconocchia Pisoni | 2024-10-30
SignIn form creation | create the view for the sign in phase | Francesco Saverio Sconocchia Pisoni | 2024-10-30
SignIn Data Validation | validate the correctness of the user's input data | Francesco Saverio Sconocchia Pisoni | 2024-10-30
JWT creation and providing | create the JWT token and provides it to the user | Francesco Saverio Sconocchia Pisoni | 2024-11-06
Profile form creation | create the view of the user's profile | Francesco Saverio Sconocchia Pisoni | 2024-10-30
Delete profile | delete user's data if requested by the user | Francesco Saverio Sconocchia Pisoni | 2024-10-30
Update profile | update and validate the user's data if changed by the user | Francesco Saverio Sconocchia Pisoni | 2024-10-30
Message consumer | create the routine which retrieves the messages from the queue | Francesco Saverio Sconocchia Pisoni | 2024-11-06
Message insertion | insert the messages in the DB once parsed | Francesco Saverio Sconocchia Pisoni | 2024-11-06
Tests auth | create the unit tests for the authentication system routes | Francesco Saverio Sconocchia Pisoni | 2024-11-06
Home page view | create the view for the home page | Lorenzo Tanzi | 2024-10-31
Search view | create view for search results | Lorenzo Tanzi | 2024-10-31
Recipe API request "by recipe name" | implement API request by recipe name and response management | Lorenzo Tanzi | 2024-10-31
Recipe API request "by ingredient" | implement API request by ingredient and response management | Lorenzo Tanzi | 2024-10-31
Insertion of saved recipe | implement query to insert recipes into favourites recipes | Lorenzo Tanzi | 2024-11-08
Saved recipes view | create view to display all saved recipes | Lorenzo Tanzi | 2024-11-08
Recipe view | create view to display all information of a recipe | Lorenzo Tanzi | 2024-11-08
Removal of saved recipe | implement query to delete recipes from favourites recipes | Lorenzo Tanzi | 2024-11-08
Create shopping list | Develop the view for the shopping list | Giulio Caporro | 2024-11-08
Implement Ingredient Selection | Code the functionality to allow users to select multiple ingredients from the shopping list. | Giulio Caporro | 2024-11-08
Add Quantity Selection | Add functionality for users to specify quantities of each selected ingredient before moving to storage. | Giulio Caporro | 2024-11-08
Create Delete Option in Shopping List View | Add a delete option next to each ingredient in the shopping list view. | Giulio Caporro | 2024-11-08
Implement Ingredient Deletion Function | Code the function that deletes selected ingredients from the shopping list in the database. | Giulio Caporro | 2024-11-08
Validation for Delete Action | Add validation to confirm the deletion action (ask for confirmation if multiple items are selected). | Giulio Caporro | 2024-11-08
Update Shopping List Display | Refresh the shopping list view to reflect changes after ingredients are deleted. | Giulio Caporro | 2024-11-08
Move Ingredients to Storage | Code the functionality to move ingredients from the shopping list to the ingredients storage, updating quantities. | Giulio Caporro | 2024-11-08
Validate Quantity Update | Add a validation step to ensure that moved ingredients update the quantity correctly in storage. | Giulio Caporro | 2024-11-08
Display Shopping List Details | Develop a feature to display detailed information for each shopping list, including items and quantities. | Giulio Caporro | 2024-11-08
RabbitMQ service | Create the microservice of RabbitMQ with its configuration file | Francesco Saverio Sconocchia Pisoni | 2024-11-10
Notification service | Create the Notification project | Francesco Saverio Sconocchia Pisoni | 2024-11-10
Filters | Set the security configurations of the Notification service | Francesco Saverio Sconocchia Pisoni | 2024-11-10
Notification implementation | Create and implement the api routes of the Notification service | Francesco Saverio Sconocchia Pisoni | 2024-11-10
Create Storage Model | Implement the data model for the storage service | Giulio Caporro | 2024-12-01
Implement CRUD operations | Create the basic CRUD operations for the storage service | Giulio Caporro | 2024-12-01
JWT Integration for Security | Secure the storage service endpoints using JWT-based authentication | Giulio Caporro | 2024-12-01
Create Scheduled Task Service | Develop a scheduled task to check for expired products and perform notifications | Giulio Caporro | 2024-12-01
Notification Integration | Integrate the notification service to alert users about expired products | Giulio Caporro | 2024-12-01
Implement UI | Design and implement the user interface for managing the storage service | Lorenzo Tanzi | 2024-12-01
Set Expiration Date for Ingredients | Add functionality to allow users to set expiration dates for ingredients in their storage. | Giulio Caporro | 2024-12-01
Enable Notifications for Expirations | Code the logic to send notifications 1 day before an ingredient expires. | Giulio Caporro | 2024-12-01
Add Quantity Selection for Storage | Develop functionality to allow users to set and update the quantity of each ingredient in storage. | Giulio Caporro | 2024-12-01
Display Ingredient Storage | Create a feature to display all ingredients available in the user's storage, along with their details. | Giulio Caporro | 2024-12-01